## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a student, I want to upload my resume so that the system can analyze it. | MUST HAVE | Resume parser | Dharma Teja | 3- Completed
Sprint 1 | sprint1 | US02 | As a student, I want the system to extract my details from my resume so that my profile can be created automatically. | MUST HAVE | Resume Upload | Dharma Teja | 3- Completed
Sprint 1 | Sprint1 | US03 | As a student, I want my resume to be analyzed so that I can understand its strengths, weaknesses, and overall score. | MUST HAVE | Resume Analysis | Dharma Teja | 3- Completed
Sprint 1 | sprint 1 | US04 | As a student, I want to receive career role recommendations based on my resume so that I can identify suitable career options | MUST HAVE | Candidate Profile | Dharma Teja | 3- Completed
Sprint 1 | Sprint 1 | US05 | As a student, I want to identify my skill gaps for a recommended career role so that I know which skills I need to improve. | MUST HAVE | Career Recommendations | Dharma Teja | 3- Completed
Sprint 1 | Sorint 1 | US06 | As a student, I want to receive interview questions and preparation tips based on my recommended career role so that I can prepare for interviews. | MUST HAVE | career Recommendations | Dharma Teja | 3- Completed
Sprint 1 | Sprint 1 | US07 | As a student, I want the system to use multiple AI agents for resume analysis, career recommendations, skill-gap analysis, and interview preparation so that I can receive comprehensive career assistance. | MUST HAVE | AI Agents | Dharma Teja | 3- Completed
Sprint 2 | sprint2 | Us08 | As a student, I want the system to have a curated internship job knowledge base so that relevant job opportunities can be retrieved. | MUST HAVE | Job Dataset | Dharma Teja | 3- Completed
Sprint2 | Sprint 2 | Us09 | As a student, I want job postings to be chunked and converted into embeddings so that the system can perform semantic search. | MUST HAVE | Internship Knowledge Base | Dharma Teja | 3- Completed
Sprint 2 | Sprint 2 | US10 | As a student, I want job postings to be embedded and indexed so that the system can perform semantic search. | MUST HAVE | Job Embeddings and FAISS Index | Dharma Teja | 3- Completed
Sprint 2 | Sprint 2 | US11 | As a student, I want the system to compare my resume with retrieved job postings so that I can understand how well I match each opportunity. | MUST HAVE | Semantic Job Retrieval | Dharma Teja | 3- Completed
Sprint 2 | Sprint 2 | US12 | As a student, I want each matched job to have a compatibility score with an explanation of matching and missing skills so that I can understand why the job is suitable for me. | MUST HAVE | Job-Resume Matching Agent | Dharma Teja | 3- Completed
Sprint 3 | Sprint 3 | US13 | As a student, I want the system to analyze my skill gaps against a selected job so that I know which skills I need to improve. | MUST HAVE | Candidate Profile and Selected Job | Dharma Teja | 3- Completed
Sprint 3 | Sprint 3 | US14 | As a student, I want to customize my resume and generate a role-specific cover letter so that I can apply for relevant opportunities. | MUST HAVE | Candidate Profile and Selected Job | Dharma Teja | 3- Completed
Sprint 3 | Sprint 3 | US15 | As a student, I want personalized interview preparation based on my profile and selected job so that I can prepare effectively for interviews. | MUST HAVE | Candidate Profile and Skill Gap Analysis | Dharma Teja | 3- Completed
Sprint 3 | Sprint 3 | US16 | As a student, I want to practice through a mock interview so that I can improve my interview readiness. | MUST HAVE | Interview Preparation | Dharma Teja | 3- Completed
Sprint 3 | Sprint 3 | US17 | As a student, I want to ask career-related questions conversationally so that I can receive personalized career guidance. | MUST HAVE | Candidate Profile, Job Matching, Skill Gap and Interview Preparation | Dharma Teja | 3- Completed
Sprint 4 | Sprint 4 | US19 | As a student, I want to add job and internship applications so that I can maintain a record of my application | MUST HAVE | Student Profile | Dharma Teja | Completed
Sprint 4 | Sprint 4 | US20 | As a student, I want to view my saved applications so that I can monitor all my applications in one place. | MUST HAVE | Application Record | Dharma Teja | Completed
Sprint 4 | Sprint 4 | US21 | As a student, I want to update my application status so that I can track recruitment progress | MUST HAVE | Application Record | Dharma Teja | Completed
Sprint 4 | Sprint 4 | US22 | As a student, I want to record important application dates and notes so that I can organize my recruitment activities. | SHOULD HAVE | Application Records | Dharma Teja | Completed
Sprint 4 | Sprint 4 | US23 | As a student, I want to edit or remove an application record so that I can maintain accurate application information | SHOULD HAVE | Application Records | Dharma Teja | Completed*
Sprint 4 | Sprint 4 | US24 | As a student, I want to access application tracking from the existing Career Companion application so that I can manage my applications in one place. | MUST HAVE | Flask Application | Dharma Teja | Completed*
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Research and understand requirements for the AI Career Companion | 2026-08-26 | 2026-08-26 | Dharma Teja | Research | Completed | 4 hours | Day 1: Research and understand project requirements
US02 | T02 | Implement resume upload and PDF text extraction | 2026-08-27 | 2026-08-27 | Dharma Teja | Development | Completed | 6 hours | Day 2: Resume upload and PDF text extraction
US03 | T03 | Implement resume analysis and scoring using Gemini LLM | 2026-08-27 | 2026-08-27 | Dharma Teja | Development | 3- Completed | 7 hours | Day 3: Resume analysis and scoring
US04 | T04 | Implement career role recommendation agent | 2026-08-29 | 2026-08-29 | Dharma Teja | Development | 3- Completed | 5 hours | Day 4: Career recommendation agent
US05 | T05 | Implement skill gap analysis agent | 2026-08-30 | 2026-08-30 | Dharma Teja | Development | 3- Completed | 6 hours | Day 5: Skill gap analysis agent
US06 | T06 | Implement interview preparation agent | 2026-08-31 | 2026-08-31 | Dharma Teja | Development | 3- Completed | 7 hours | Day 6: Interview preparation agent
US07 | T07 | AI agents with the Flask application and perform end-to-end testing | 2026-09-01 | 2026-09-02 | Dharma Teja | Integration | 3- Completed | 8 hours | Day 7: AI agent integration and end-to-end testing
US08 | T08 | Prepare and curate the internship job posting dataset | 2026-09-04 | 2026-09-04 | Dharma Teja | Dharma Teja | Completed | 6 hours | Day 1: Research and dataset preparation
US09 | T09 | Clean and preprocess the curated job posting dataset | 2026-09-05 | 2026-09-05 | Dharma Teja | Development | Completed | 5 hours | Day 2: Clean and preprocess job dataset
US09 | T10 | Split job postings into searchable text chunks for semantic retrieval | 2026-09-06 | 2026-09-06 | Dharma Teja | Development | Completed | 5 hours | Day 3: Split job postings into searchable chunks
US09 | T11 | Generate embeddings for job posting chunks for semantic retrieval | 2026-09-07 | 2026-09-07 | Dharma Teja | Development | 3- Completed | 6 hours | Day 4: Generate embeddings for job chunks
US09 | T12 | Build FAISS vector index for job posting embeddings | 2026-09-08 | 2026-09-08 | Dharma Teja | Development | 3-Completed | 5 hours | Day 5: Build FAISS vector index
US10 | T13 | Implement semantic job retrieval agent using the FAISS index | 2026-09-09 | 2026-09-09 | Dharma Teja | Development | 3-Completed | 6 hours | Day 6: Implement semantic job retrieval agent
US11 | T14 | Implement job-resume matching agent to compare candidate profiles with retrieved jobs | 2026-09-10 | 2026-09-10 | Dharma Teja | Development | 3-Completed | 6 hours | Day 7: Implement job-resume matching agent
US12 | T15 | Add compatibility scoring and explanations for matched jobs | 2026-09-11 | 2026-09-11 | Dharma Teja | Development | 3-Completed | 5 hours | Day 8: Add compatibility scoring and explanations
US12 | T16 | Validate job retrieval and matching results using sample student profiles | 2026-09-12 | 2026-09-13 | Dharma Teja | Testing | 3-Completed | 5 hours | Day 9: Validate retrieval and matching results
US10 | T17 | Integrate job retrieval and matching agents with the Flask application | 2026-09-13 | 2026-09-13 | Dharma Teja | Integration | 3-Completed | 6 hours | Day 10: Integrate agents with Flask application
US12 | T18 | Implement Skill Gap Analysis Agent and compare candidate skills with selected job requirements | 2026-09-14 | 2026-09-14 | Dharma Teja | Development | 3-Completed | 7 hours
US13 | T19 | Implement Resume and Cover Letter Customization Agent | 2026-09-15 | 2026-09-15 | Dharna Teja | Development | 3- Completed | 7 hours
US14 | T20 | Implement Interview Preparation Agent with technical, resume, project, role-specific and HR questions | 2026-09-16 | 2026-09-16 | Dharna Teja | Development | 3- Completed | 7 hours
US15 | T21 | Implement interactive Mock Interview workflow | 2026-09-17 | 2026-09-17 | Dharna Teja | Development | 3- Completed | 6 hours
US16 | T22 | Implement Conversational Career Assistant and integrate career context | 2026-09-18 | 2026-09-18 | Dharna Teja | Development | 3- Completed | 7 hours
US17 | T23 | Integrate conversation history and retrieved job information with Career Assistant | 2026-09-19 | 2026-09-19 | Dharna Teja | Integration | 3- Completed | 6 hours
US18 | T24 | Test and validate all Milestone 3 agents and workflows | 2026-09-20 | 2026-09-20 | Dharna Teja | Testing | 3- Completed | 6 hours
US19 | T25 | Review requirements and plan the Application Tracking Module | 2026-09-21 | 2026-09-21 | Dharma Teja | Research | Completed | 3 hours
US19 | T26 | Design the application tracking interface | 2026-09-22 | 2026-09-23 | Dharma Teja | Design | Completed* | 4 hours
US19 | T27 | mplement adding and saving application records | 2026-09-24 | 2026-09-25 | Dharma Teja | Development | Completed* | 6 hours
US20 | T28 | Implement displaying saved application records | 2026-09-26 | 2026-09-27 | Dharma Teja | Development | Completed | 4 hours
US21 | T29 | Implement updating application status | 2026-09-28 | 2026-09-29 | Dharma Teja | Development | Completed | 4 hours
US22 | T30 | Implement application date and notes management | 2026-09-30 | 2026-10-01 | Dharma Teja | Development | Completed* | 4 hours
US23 | T31 | Implement editing and deleting application record | 2026-10-02 | 2026-10-03 | Dharma Teja | Development | Completed* | 4 hours
US24 | T32 | Integrate the Application Tracking Module with the Flask application | 2026-10-04 | 2026-10-05 | Dharma Teja | Integration | Completed | 5 hours
US25 | T33 | Test application tracking workflows and resolve identified issues | 2026-10-06 | 2026-10-06 | Dharma Teja | Testing | Completed | 5 hours
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Understanding project requirements | Discussed and clarified the requirements and planned the implementation
Sprint 1 | Day 2 | PDF text extraction needed to be implemented | Implemented PDF resume upload and text extraction using PyPDF2
Sprint 1 | Day 3 | Resume analysis and scoring needed to be integrated with the LLM | Implemented resume analysis and scoring using Gemini LLM
Sprint 1 | Day 4 | Career recommendation logic needed to be implemented | Implemented the career role recommendation agent
Sprint 1 | Day 5 | Skill gap analysis needed to be implemented based on recommended roles | Implemented the skill gap analysis agent
Sprint 1 | Day 6 | Interview preparation needed to be personalized for the candidate | Implemented the interview preparation agent
Sprint 1 | Day 7 | Multiple AI agents needed to work together in the Flask application | Integrated the AI agents and performed end-to-end testing
Sprint 2 | Day 1 | Internship job dataset needed to be prepared for the RAG pipeline | Curated and prepared the internship job posting dataset
Sprint 2 | Day 2 | Raw job postings contained missing and inconsistent data | Cleaned and preprocessed the job posting dataset
Sprint 2 | Day 3 | Job postings needed to be divided into smaller sections for semantic retrieval | Split the job postings into searchable text chunks
Sprint 2 | Day 4 | Job chunks needed vector representations for semantic search | Generated embeddings for the job posting chunks
Sprint 2 | Day 5 | Job embeddings needed to be indexed for efficient similarity search | Built the FAISS vector index using the generated embeddings
Sprint 2 | Day 6 | Relevant jobs needed to be retrieved based on the candidate profile | Implemented the semantic job retrieval agent using the FAISS index
Sprint 2 | Day 7 | Retrieved jobs needed to be compared with the candidate profile | Implemented the job-resume matching agent
Sprint 2 | Day 8 | Matching results needed a clear compatibility score and explanatio | Added compatibility scoring with matching skills, missing skills, and reasoning
Sprint 2 | Day 9 | Retrieval and matching results needed to be validated | Tested the retrieval and matching pipeline using sample student profiles
Sprint 2 | Day 10 | Retrieval and matching agents needed to be integrated into the existing application | Integrated the job retrieval and matching agents with the Flask application and completed end-to-end testing
Sprint 3 | Day 1 | Skill gap analysis needed to compare the candidate profile with selected job requirements | Implemented and integrated the Skill Gap Analysis Agent
Sprint 3 | Day 2 | Resume and cover letter needed to be customized for selected roles | Implemented the Resume & Cover Letter Customization Agent
Sprint 3 | Day 3 | Interview preparation needed to be more specific to the selected job | Implemented the Interview Preparation Agent
Sprint 3 | Day 4 | Interview practice workflow needed to be added | Implemented and tested the Mock Interview feature
Sprint 3 | Day 5 | Career Assistant needed to combine information from multiple agents | Implemented the Conversational Career Assistant
Sprint 3 | Day 6 | Career Assistant needed access to previous conversation context and retrieved job information | Integrated conversation history and RAG/job retrieval context
Sprint 3 | Day 7 | M3 components needed end-to-end validation | Tested Skill Gap, Resume/Cover Letter, Interview Preparation, Mock Interview and Career Assistant workflows
| Day 1 | Application tracking requirements needed to be finalized. | Reviewed the requirements and identified the application details to manage.
Sprint 4 | Day 2 | The application tracking interface needed to be designed | Designed the interface for displaying and managing application records.
Sprint 4 | Day 3 | Application details needed to be stored and retrieved. | Implemented the application record management functionality.
Sprint 4 | Day 4 | Users needed to monitor application progress | Implemented application status management
Sprint 4 | Day 5 | The module needed to work with the existing application. | Integrated the tracking module with the existing Flask application.
Sprint 4 | Day 6 | Application tracking workflows needed validation | Tested the supported workflows and corrected identified issues.
Sprint 4 | Day 7 | The final milestone needed review and demonstration preparation. | Reviewed the module and prepared the demonstration.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-26 | 2026-09-03 | Dharma Teja | Plan tasks clearly before implementation | Spending too much time on minor implementation issues | Regular testing after completing each feature | Followed a planned task sequence and tested the implemented features
2 | Sprint 2 | 2026-09-04 | 2026-09-13 | Dharma Teja | Validate retrieval and matching results with sample profiles | Making changes without testing the complete pipeline | Testing each component before integration | Tested the RAG pipeline and integrated the retrieval and matching features with the Flask application
3 | Sprint 3 | 2026-09-14 | 2026-09-24 | Dharma Teja | Validate agent outputs with different scenarios before final integration | Making UI/code changes without checking the complete workflow | Testing each agent individually and then testing the integrated system | Implemented and tested the M3 agents, fixed integration/display issues, and validated the complete career-assistance workflow
4 | Sprint 4 | 2026-09-25 | 2026-10-04 | Dharma Teja | Validate application records and status updates using different test scenarios. | Making changes without testing the complete application workflow. | Testing individual features before testing the integrated application. | Reviewed and tested the Application Tracking Module, checked its integration, and addressed identified issues.
5
6
7