## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Dharma Teja | 2026-09-17 | Mock interview page generated a BuildError because the mock interview route was not defined correctly | Sprint 3 | Dharma Teja | Functional | Added and corrected the mock interview route and URL mapping. | 2026-09-17 | Closed | Mock interview page opened successfully after the route was corrected.
2 | Dharma Teja | 2026-09-17 | Mock interview encountered an undefined m3_mock_interview_agent reference. | Sprint 3 | Dharma Teja | Functional | Corrected the agent initialization and reference in the application. | 2026-09-17 | Closed | Mock interview agent loaded correctly.
3 | Dharma Teja | 2026-09-18 | Mock interview stopped during the session because conversation state exceeded the normal Flask session storage behavior. | Sprint 3 | Dharma Teja | Integration | Configured Flask-Session and corrected session storage for mock interview state. | 2026-09-18 | Closed | Mock interview continued correctly across multiple questions.
4 | Dharma Teja | 2026-09-19 | Interview preparation guidance and skill-gap preparation were displayed as raw Python dictionary values instead of formatted information. | Sprint 3 | Dharma Teja | UI | Updated the Jinja template to display dictionary fields such as category, action, gap, status and preparation method separately. | 2026-09-19 | Closed | Preparation guidance and skill-gap preparation are now displayed clearly.
5 | Dharma Teja | 2026-09-24 | Application record was not saved correctly after submission. | Sprint 4 | Dharma Teja | Functional | Enter how you actually fixed it; if not fixed yet, write Pending investigation and correction. | 2026-09-25 | Closed | Describe the actual test result or remaining issue
6 | Dharma Teja | 2026-09-28 | Application status was not updated correctly after selecting a new status | Sprint 4 | Dharma Teja | Functional | Describe the correction, or write Pending investigation and correction. | 2026-09-29 | Closed | Record the actual retest result or explain why the issue remains open.
7 | Dharma Teja | 2026-10-02 | Application records were not displayed correctly in the application tracking interface. | Sprint 4 | Dharma Teja | UI | Describe the correction, or write Pending investigation and correction. | 2026-10-03 | Closed | Record whether the records displayed correctly after retesting.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others