## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a student, I want to upload my resume so that the system can analyze it. | MUST HAVE | Resume parser | Dharma Teja | 3- Completed
Sprint 1 | sprint1 | US02 | As a student, I want the system to extract my details from my resume so that my profile can be created automatically. | MUST HAVE | Resume Upload | Dharma Teja | 3- Completed
Sprint 1 | Sprint1 | US03 | As a student, I want my resume to be analyzed so that I can understand its strengths, weaknesses, and overall score. | MUST HAVE | Resume Analysis | Dharma Teja | 3- Completed
Sprint 1 | sprint 1 | US04 | As a student, I want to receive career role recommendations based on my resume so that I can identify suitable career options | MUST HAVE | Candidate Profile | Dharma Teja | 3- Completed
Sprint 1 | Sprint 1 | US05 | As a student, I want to identify my skill gaps for a recommended career role so that I know which skills I need to improve. | MUST HAVE | Career Recommendations | Dharma Teja | 3- Completed
Sprint 1 | Sorint 1 | US06 | As a student, I want to receive interview questions and preparation tips based on my recommended career role so that I can prepare for interviews. | MUST HAVE | career Recommendations | Dharma Teja | 3- Completed
Sprint 1 | Sprint 1 | US07 | As a student, I want the system to use multiple AI agents for resume analysis, career recommendations, skill-gap analysis, and interview preparation so that I can receive comprehensive career assistance. | MUST HAVE | AI Agents | Dharma Teja | 3- Completed
Sprint 2 | sprint2 | Us08 | As a student, I want the system to have a curated internship job knowledge base so that relevant job opportunities can be retrieved. | MUST HAVE | Job Dataset | Dharma Teja | 3- Completed
Sprint2 | Sprint 2 | Us09 | As a student, I want job postings to be chunked and converted into embeddings so that the system can perform semantic search. | MUST HAVE | Internship Knowledge Base | Dharma Teja | 3- Completed
Sprint 2 | Sprint 2 | US10 | As a student, I want the system to retrieve relevant internship roles based on my skills and profile so that I can find suitable job opportunities | MUST HAVE | Job Embeddings and FAISS Index | Dharma Teja | 3- Completed
Sprint 2 | Sprint 2 | US11 | As a student, I want the system to compare my resume with retrieved job postings so that I can understand how well I match each opportunity. | MUST HAVE | Semantic Job Retrieval | Dharma Teja | 3- Completed
Sprint 2 | Sprint 2 | US12 | As a student, I want each matched job to have a compatibility score with an explanation of matching and missing skills so that I can understand why the job is suitable for me. | MUST HAVE | Job-Resume Matching Agent | Dharma Teja | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Research and understand requirements for the AI Career Companion | 2026-08-26 | 2026-08-26 | Dharma Teja | Research | Completed | 4 hours | Day 1: Research and understand project requirements
US02 | T02 | Implement resume upload and PDF text extraction | 2026-08-27 | 2026-08-27 | Dharma Teja | Development | Completed | 6 hours | Day 2: Resume upload and PDF text extraction
US03 | T03 | Implement resume analysis and scoring using Gemini LLM | 2026-08-27 | 2026-08-27 | Dharma Teja | Development | 3- Completed | 7 hours | Day 3: Resume analysis and scoring
US04 | T04 | Implement career role recommendation agent | 2026-08-29 | 2026-08-29 | Dharma Teja | Development | 3- Completed | 5 hours | Day 4: Career recommendation agent
US05 | T05 | Implement skill gap analysis agent | 2026-08-30 | 2026-08-30 | Dharma Teja | Development | 3- Completed | 6 hours | Day 5: Skill gap analysis agent
US06 | T06 | Implement interview preparation agent | 2026-08-31 | 2026-08-31 | Dharma Teja | Development | 3- Completed | 7 hours | Day 6: Interview preparation agent
US07 | T07 | AI agents with the Flask application and perform end-to-end testing | 2026-09-01 | 2026-09-02 | Dharma Teja | Integration | 3- Completed | 8 hours | Day 7: AI agent integration and end-to-end testing
US08 | T08 | Prepare and curate the internship job posting dataset | 2026-09-04 | 2026-09-04 | Dharma Teja | Dharma Teja | Completed | 6 hours | Day 1: Research and dataset preparation
US09 | T09 | Clean and preprocess the curated job posting dataset | 2026-09-05 | 2026-09-05 | Dharma Teja | Development | Completed | 5 hours | Day 2: Clean and preprocess job dataset
US09 | T10 | Split job postings into searchable text chunks for semantic retrieval | 2026-09-06 | 2026-09-06 | Dharma Teja | Development | Completed | 5 hours | Day 3: Split job postings into searchable chunks
US09 | T11 | Generate embeddings for job posting chunks for semantic retrieval | 2026-09-07 | 2026-09-07 | Dharma Teja | Development | 3- Completed | 6 hours | Day 4: Generate embeddings for job chunks
US09 | T12 | Build FAISS vector index for job posting embeddings | 2026-09-08 | 2026-09-08 | Dharma Teja | Development | 3-Completed | 5 hours | Day 5: Build FAISS vector index
US10 | T13 | Implement semantic job retrieval agent using the FAISS index | 2026-09-09 | 2026-09-09 | Dharma Teja | Development | 3-Completed | 6 hours | Day 6: Implement semantic job retrieval agent
US11 | T14 | Implement job-resume matching agent to compare candidate profiles with retrieved jobs | 2026-09-10 | 2026-09-10 | Dharma Teja | Development | 3-Completed | 6 hours | Day 7: Implement job-resume matching agent
US12 | T15 | Add compatibility scoring and explanations for matched jobs | 2026-09-11 | 2026-09-11 | Dharma Teja | Development | 3-Completed | 5 hours | Day 8: Add compatibility scoring and explanations
US12 | T16 | Validate job retrieval and matching results using sample student profiles | 2026-09-12 | 2026-09-13 | Dharma Teja | Testing | 3-Completed | 5 hours | Day 9: Validate retrieval and matching results
US10 | T17 | Integrate job retrieval and matching agents with the Flask application | 2026-09-13 | 2026-09-13 | Dharma Teja | Integration | 3-Completed | 6 hours | Day 10: Integrate agents with Flask application
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Understanding project requirements | Discussed and clarified the requirements and planned the implementation
Sprint 1 | Day 2 | PDF text extraction needed to be implemented | Implemented PDF resume upload and text extraction using PyPDF2
Sprint 1 | Day 3 | Resume analysis and scoring needed to be integrated with the LLM | Implemented resume analysis and scoring using Gemini LLM
Sprint 1 | Day 4 | Career recommendation logic needed to be implemented | Implemented the career role recommendation agent
Sprint 1 | Day 5 | Skill gap analysis needed to be implemented based on recommended roles | Implemented the skill gap analysis agent
Sprint 1 | Day 6 | Interview preparation needed to be personalized for the candidate | Implemented the interview preparation agent
Sprint 1 | Day 7 | Multiple AI agents needed to work together in the Flask application | Integrated the AI agents and performed end-to-end testing
Sprint 2 | Day 1 | Internship job dataset needed to be prepared for the RAG pipeline | Curated and prepared the internship job posting dataset
Sprint 2 | Day 2 | Raw job postings contained missing and inconsistent data | Cleaned and preprocessed the job posting dataset
Sprint 2 | Day 3 | Job postings needed to be divided into smaller sections for semantic retrieval | Split the job postings into searchable text chunks
Sprint 2 | Day 4 | Job chunks needed vector representations for semantic search | Generated embeddings for the job posting chunks
Sprint 2 | Day 5 | Job embeddings needed to be indexed for efficient similarity search | Built the FAISS vector index using the generated embeddings
Sprint 2 | Day 6 | Relevant jobs needed to be retrieved based on the candidate profile | Implemented the semantic job retrieval agent using the FAISS index
Sprint 2 | Day 7 | Retrieved jobs needed to be compared with the candidate profile | Implemented the job-resume matching agent
Sprint 2 | Day 8 | Matching results needed a clear compatibility score and explanatio | Added compatibility scoring with matching skills, missing skills, and reasoning
Sprint 2 | Day 9 | Retrieval and matching results needed to be validated | Tested the retrieval and matching pipeline using sample student profiles
Sprint 2 | Day 10 | Retrieval and matching agents needed to be integrated into the existing application | Integrated the job retrieval and matching agents with the Flask application and completed end-to-end testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-26 | 2026-09-03 | Dharma Teja | Plan tasks clearly before implementation | Spending too much time on minor implementation issues | Regular testing after completing each feature | Followed a planned task sequence and tested the implemented features
2 | Sprint 2 | 2026-09-04 | 2026-09-13 | Dharma Teja | Validate retrieval and matching results with sample profiles | Making changes without testing the complete pipeline | Testing each component before integration | Tested the RAG pipeline and integrated the retrieval and matching features with the Flask application
3
4
5
6
7